MAILLOT STORE

Implementation Roadmap & Project Control Document

Retail Management & E-commerce System

| Version | 1.0 |
| --- | --- |
| Status | Implementation Baseline |
| Repository | maillot-store |
| Purpose | Guide implementation from repository setup through deployment and handover |

# 1. Purpose

This document is the implementation roadmap for the Maillot Store Retail Management & E-commerce System. It keeps development organized, defines the intended sequence from foundation through deployment, and provides a control reference when development begins to deviate from the approved direction.

It is based on the Business/Brand Identity, Project Planning Document (PPD), Solution Proposal, Software Requirements Specification (SRS), System Design Document (SDD), Database Design Document (DBD), and Website Checklist.

# 2. Implementation Baseline

The PPD defines the project lifecycle as Business Discovery → Project Planning → SRS → SDD → Client Functional Overview → User Interface Design → System Development → Testing → Deployment → Maintenance.

The planning, requirements, solution proposal, system design and database design documents are already prepared. The project is therefore entering the UI/UX Design and System Development stages.

# 3. Source-of-Truth Rules

Business & Brand Identity: business direction, brand personality, target audience, sales channels and customer-facing identity.

PPD: project lifecycle, objectives, scope, deliverables, risks and success criteria.

Solution Proposal: proposed solution and Version 1 scope.

SRS: what the system must do, including functional/non-functional requirements and business rules.

SDD: how the system is technically structured, including architecture, modules, APIs, UI areas, security and deployment.

DBD: database entities, relationships, constraints, naming standards, audit strategy and data integrity.

Website Checklist: additional frontend UX/conversion guidance. Its coaching-specific wording must be adapted to Maillot Store.

# 4. Technology Baseline

| Area | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js, React, TypeScript | Customer, influencer and administration interfaces |
| UI | Tailwind CSS, shadcn/ui | Responsive and consistent components |
| Backend | NestJS, TypeScript | REST API and business logic |
| Database | PostgreSQL | Central business data store |
| ORM | Prisma | Database access, schema and migrations |
| API Documentation | Swagger / OpenAPI | API documentation and testing |
| Deployment | Docker, Nginx, Vercel (frontend) | Production architecture |

# 5. Complete Implementation Flow

01. Phase 0 — Project Foundation

02. Phase 1 — UI/UX Design & Design System

03. Phase 2 — Database & Prisma

04. Phase 3 — Backend Foundation

05. Phase 4 — Authentication & RBAC

06. Phase 5 — Product & Catalogue Management

07. Phase 6 — Customer Management

08. Phase 7 — Inventory Management

09. Phase 8 — Supplier & Purchase Management

10. Phase 9 — Order Management

11. Phase 10 — Payment Management

12. Phase 11 — Delivery Management

13. Phase 12 — Influencer Programme

14. Phase 13 — CMS / Website Content

15. Phase 14 — Reporting & Analytics

16. Phase 15 — Complete Frontend Integration

17. Phase 16 — Full Testing & Security

18. Phase 17 — Deployment

19. Phase 18 — Documentation, Handover & Maintenance

# 6. Detailed Phase Plan

## Phase 0 — Project Foundation

Clone and verify the GitHub repository.

Keep the existing Docs folder intact and version-controlled.

Create client, server, database and scripts workspace folders.

Confirm Node.js, package manager, Git, PostgreSQL, Docker and development tooling.

Create project README and environment-variable strategy.

Do not begin feature development until the repository foundation is stable.

## Phase 1 — UI/UX Design & Design System

Define colours, typography, spacing, buttons, cards, forms and navigation.

Design the public storefront: Home, Shop, Categories, Product Details, Promotions, About, Contact, Cart and Checkout.

Design Customer, Influencer and Administration portals.

Apply the Website Checklist principles: clear messaging, simple navigation, visible primary actions, credibility/trust, logical flow and strong mobile experience.

Adapt the checklist to e-commerce; do not copy coaching-specific content or CTAs.

Validate the main customer journey before detailed UI implementation.

## Phase 2 — Database & Prisma

Set up PostgreSQL and Prisma.

Implement DBD entities and relationships.

Apply UUID primary keys, plural table names and snake_case columns.

Apply audit fields and soft-delete strategy.

Implement foreign keys, unique constraints and inventory integrity rules.

Create migrations and controlled seed data.

## Phase 3 — Backend Foundation

Create the NestJS application.

Establish Controller → DTO/Validation → Service → Repository → Prisma.

Configure database access, environment configuration, errors, logging, CORS and API versioning.

Configure Swagger/OpenAPI and common backend utilities.

## Phase 4 — Authentication & RBAC

Registration, login, logout/session handling and password reset.

Secure password hashing and JWT authentication.

Implement roles and permissions and protect endpoints with RBAC.

Seed and verify Administrator, Staff, Customer and Influencer roles.

## Phase 5 — Product & Catalogue Management

Categories, brands, products, variants, sizes, colours, editions and images.

Product activation/archive behaviour.

Administration product management UI.

Customer-facing catalogue, search and filtering.

## Phase 6 — Customer Management

Customer profiles and multiple delivery addresses.

Order history, settings and notifications where required.

Guest checkout support and customer-facing account UI.

## Phase 7 — Inventory Management

Inventory per product variant and inventory movements.

Purchases, sales, returns, damage, loss and adjustments.

Low-stock thresholds and alerts.

Prevent negative inventory and keep stock consistent across sales channels.

## Phase 8 — Supplier & Purchase Management

Supplier records, purchases, purchase items and purchase history.

Connect confirmed purchases to inventory increases.

Build administration screens for supplier and purchase operations.

## Phase 9 — Order Management

Website, walk-in, WhatsApp and phone orders.

Unique order numbers and order-source tracking.

Order statuses and cancellation.

Connect confirmed orders to inventory deduction.

Customer order tracking and notifications where required.

## Phase 10 — Payment Management

Payment records and payment status.

Support the approved Version 1 payment methods.

Link every payment to an order.

Do not mark orders paid before payment confirmation.

Payment history and receipts where required; keep provider integrations modular.

## Phase 11 — Delivery Management

Delivery records, third-party assignment, tracking information and statuses.

Connect delivery completion to order status.

Customer-facing delivery tracking.

## Phase 12 — Influencer Programme

Influencer registration and administrator approval.

Unique referral codes/links and referral sales tracking.

Automatic commission calculation and historical commission preservation.

Commission balance, withdrawal requests and administration processing.

## Phase 13 — CMS / Website Content

Homepage banners, promotions and featured products.

About Us and Contact information.

Allow authorized administrators to update public content without source-code changes.

## Phase 14 — Reporting & Analytics

Sales, inventory, revenue, influencer commission and customer reports where required.

Dashboard statistics using system data.

Restrict reports to authorized users.

## Phase 15 — Complete Frontend Integration

Connect storefront, customer portal, influencer portal and administration portal to real APIs.

Replace development placeholders/mock data with real data.

Complete responsive behaviour on mobile, tablet and desktop.

Verify browsing → cart → checkout → payment → order → delivery tracking.

## Phase 16 — Full Testing & Security

Unit, integration and end-to-end testing.

Authentication, authorization, validation and security testing.

Inventory, order/payment and commission business-rule testing.

Responsive UI and browser compatibility testing.

Fix defects before deployment.

## Phase 17 — Deployment

Prepare production environment variables.

Deploy PostgreSQL and run migrations.

Deploy NestJS backend and Next.js frontend.

Configure domain, HTTPS, CORS and reverse proxy where applicable.

Configure backups, logging, monitoring and error tracking.

Run production smoke tests.

## Phase 18 — Documentation, Handover & Maintenance

Complete technical, API, database and deployment documentation.

Prepare user/admin manual.

Verify deliverables against the PPD and Solution Proposal.

Establish controlled maintenance and future-enhancement process.

# 7. Standard Development Cycle for Every Feature

Requirement — identify the exact SRS/business requirement.

Design — verify the relevant SDD architecture and workflow.

Data — verify the DBD entity, relationship, constraints and audit requirements.

Database — implement/update Prisma schema and migration.

Backend — implement DTOs, validation, repository, service and controller.

API Test — verify endpoint behaviour and business rules.

Frontend — build the UI using the approved UX/design direction.

Integration — connect the UI to the real API.

End-to-End Test — test the complete user/business flow.

Review — confirm the feature matches the requirement and does not break existing modules.

Commit — create a clear Git commit.

Progress Update — mark the feature/phase complete before moving forward.

# 8. Phase Completion Gate

A phase is complete only when:

Relevant requirements are satisfied.

Architecture and database design are respected.

Business rules are enforced.

Feature/module has been tested.

Frontend works with the real backend where applicable.

No unresolved issue threatens the next phase.

Work is committed to Git.

# 9. Deviation Control

If development starts moving away from this roadmap:

STOP — do not continue the disputed work blindly.

IDENTIFY — state exactly what changed.

TRACE — identify the affected source document.

CLASSIFY — bug fix, implementation detail, clarification, improvement or new requirement.

IMPACT — check database, API, frontend, security, timeline and existing modules.

DECIDE — keep the plan or formally update the baseline.

DOCUMENT — record important approved changes.

IMPLEMENT — continue only when the direction is clear.

# 10. Rules That Require an Explicit Decision to Change

Do not add out-of-scope Version 1 features without explicit approval.

Do not replace the documented architecture without impact assessment.

Do not contradict the DBD without documenting the reason.

Do not bypass business rules for convenience.

Do not build the entire frontend with fake data and postpone backend integration to the end.

Never store passwords in plaintext.

Never commit secrets or production credentials to GitHub.

Do not permanently delete business records where soft deletion is required.

Inventory must never become negative.

Historical influencer commissions must not change when the commission percentage changes.

Website Checklist content must be adapted to Maillot Store; coaching-specific wording is not automatically part of the project.

# 11. Version 1 Scope Boundary

Responsive e-commerce website

Customer portal

Influencer portal

Product management

Inventory management

Supplier & purchase management

Order management

Payment management

Delivery management

Reporting & analytics

Website content management

Administration dashboard

Future enhancements such as multi-branch management, native mobile apps, loyalty/rewards, gift cards, AI recommendations, multi-language, multi-currency, advanced forecasting and additional providers/couriers should not distract Version 1 unless the scope is explicitly changed.

# 12. Current Project Status

| Stage | Status | Notes |
| --- | --- | --- |
| Business Discovery | Complete | Business/brand information established. |
| Project Planning | Complete | PPD prepared. |
| Solution Proposal | Complete | Version 1 scope defined. |
| Requirements | Complete | SRS prepared. |
| System Design | Complete | SDD prepared. |
| Database Design | Complete | DBD prepared and Prisma schema implemented/extended. |
| Repository / Foundation | Complete | Git repository, client/server/database structure and backend foundation established. |
| Authentication & RBAC | Complete | Customer registration/login, JWT authentication, roles and protected endpoints verified. |
| Product / Catalogue | Backend Foundation Complete | Product, variant and catalogue backend work is present; frontend integration remains. |
| Inventory | Complete | Variant inventory, movements and stock deduction on confirmed payment/order flow tested. |
| Order Management | Complete | Order creation, order status and inventory deduction flow tested. |
| Payment Management | Complete | Payment creation, status confirmation and payment-to-order integration tested. |
| Delivery Management | Complete | Delivery creation, status progression, tracking number/provider and delivered timestamp tested. |
| Customer Rewards | Implemented (Scope Review) | Reward rules, customer rewards, awarding and redemption tested. This is outside the roadmap's original Version 1 boundary and requires an explicit scope decision. |
| Influencer Programme | In Progress | Self-registration, referral code generation, administrator approval and referral creation tested. Commission and withdrawal workflows remain. |
| CMS / Website Content | Pending | Not yet implemented. |
| Reporting & Analytics | Pending | Not yet implemented. |
| Frontend Integration | Pending | Next.js storefront, customer, influencer and administration UI integration remains. |
| Full Testing & Security | Pending | Feature tests completed progressively; full unit/integration/E2E/security pass remains. |
| Deployment | Pending | Production deployment preparation remains. |
| Handover & Maintenance | Pending | Technical/user documentation and handover remain. |

Implementation snapshot as of 12 August 2026: Backend work has progressed through Payments, Delivery and the early Influencer Programme. The most recently verified workflow is influencer self-registration → PENDING → administrator approval → ACTIVE → referral creation. Commission files have been planned but not yet implemented.

# 13. Immediate Next Steps

• Complete the Influencer Programme: commission calculation, commission history/balance, withdrawal requests and administration processing.

• Review the Customer Rewards implementation against the approved Version 1 scope and formally decide whether to retain it in Version 1 or move it to future scope.

• Continue remaining backend modules: CMS / website content and Reporting & Analytics.

• Build the Next.js responsive storefront, Customer portal, Influencer portal and Administration dashboard using real APIs.

• Complete integration testing across browsing → cart → checkout → payment → order → delivery and influencer referral → commission → withdrawal flows.

• Run the full security, validation, RBAC, inventory, payment, commission and end-to-end test pass.

• Prepare production environment, deployment, backups, monitoring and smoke tests.

• Update technical/API/database/deployment documentation and prepare handover/user-admin manuals.

• Before the next work session, commit the completed local implementation to Git with a clear feature commit and push it to GitHub.

Create the Phase 0 workspace in the cloned repository.

Verify the development environment.

Create the Next.js frontend foundation in client/.

Create the NestJS backend foundation in server/.

Create the Prisma/database foundation in database/.

Establish environment configuration and Git ignore rules.

Proceed into UI/UX design and the first implementation slice.

# 14. Project Control Reminder

If implementation begins to drift, return to this document first. Identify the current phase, compare the work against the phase objectives and source documents, and only then continue.

The roadmap may be changed when a legitimate requirement changes. The important rule is that significant deviations must be visible, understood, intentional and documented.